## Project_3_Unity
Task Name | Start Date | End Date | Duration | Predecessors | % Complete | Status | Assigned To | Comments
Gem Matching | 2016-10-23 | 2016-11-01 | 8d |  | 38% | In Progress
Display Gems | 2016-10-23 | 2016-10-23 | 1d |  | 100% | In Progress | Deema
Swap two gems | 2016-10-24 | 2016-10-24 | 1d | Display Gems | 50% | In Progress | Deema
Remove Replaced Gems | 2016-10-31 | 2016-11-01 | 2d | Swap Gems | 0% |  | Deema
Dungeon Floor | 2016-10-21 | 2016-10-22 | 1d |  | 100% | In Progress
floor tiles interlock | 2016-10-21 | 2016-10-21 | 1d |  | 100% | In Progress | Hans Brown
floor tiles can be walked upon | 2016-10-22 | 2016-10-22 | 1d | floor tiles interlock | 100% | Not Started | Hans Brown
floor tiles know what stands on them | 2016-10-21 | 2016-10-21 | 1d | floor tiles interlock | 100% | Not Started | Hans Brown
Player Character | 2016-10-21 | 2016-10-31 | 7d |  | 95% | Not Started
character appears on screen | 2016-10-21 | 2016-10-21 | 1d |  | 100% | Not Started | Hans and Cara
character can walk around freely | 2016-10-22 | 2016-10-22 | 1d | floor tiles can be walked upon | 100% | Not Started | Hans Brown
character reads player input | 2016-10-22 | 2016-10-22 | 1d | character appears on screen | 100% |  | Hans and Cara
character can attack enemies | 2016-10-31 | 2016-10-31 | 1d | character appears on screen | 100% |  | Hans Brown
character can cast spells | 2016-10-25 | 2016-10-25 | 1d | character appears on screen | 70% |  | Cara
character can rotate | 2016-10-29 | 2016-10-29 | 1d | character can walk around freely | 100% |  | Hans Brown
Monster AI | 2016-10-21 | 2016-10-29 | 6d |  | 100%
monsters appear on screen | 2016-10-21 | 2016-10-21 | 1d |  | 100% |  | Hans and Paul
monsters walk according to logic | 2016-10-29 | 2016-10-29 | 1d | monsters appear on screen | 100% |  | Hans and Paul
Documentation
Initial Documentation | 2016-10-21 | 2016-10-21 | 1d |  | 100% |  | Everyone
Project 3 Final Documentation | 2016-10-31 | 2016-10-31 | 1d |  | 80% |  | Hans Brown
Project 4 Initial Documentation | 2016-10-31 | 2016-10-31 | 1d |  | 80% |  | Paul

## Comments
Row 1 | Sample Discussion Need help? E-mail us at support@smartsheet.com or call us at 425.283.1870 | Todd Jones | 08/28/13 11:58 AM
| This is a sample discussion. Discussions will let you track comments about a particular line item or sheet. Many customers paste relevant emails into a discussion as well. | Todd Jones | 08/28/13 11:59 AM